## SFT MIDP Template
Scottish Fututres Trust - Master Information Delivery Plan (MIDP) Template
Project Number
Project Title
Author | [10 empty] | Example file name
Date Created
Date Last Updated
Document Reference | [25 empty] | OWNER | INSERT NAME OF OWNER
|  |  | Refer to file naming convention doc for info | [6 empty] | OPTIONAL |  | DATA EXCHANGE #01 |  | DATA EXCHANGE #02 |  | DATA EXCHANGE #03 |  | DATA EXCHANGE #04 |  | DATA EXCHANGE #05 |  | DATA EXCHANGE #06 |  | DATA EXCHANGE #07 |  | Client
|  |  | FILE NAME | [8 empty] | STAGE: | BRIEF | STAGE: | CONCEPT | STAGE: | DEFINITION | STAGE: | DESIGN | STAGE: | BUILD AND COMMISSION | STAGE: | HANDOVER AND CLOSE OUT | STAGE: | OPERATION IN USE | Client adviser
[12 empty] | PROGRAMME REF: |  | PROGRAMME REF: |  | PROGRAMME REF: |  | PROGRAMME REF: |  | PROGRAMME REF: |  | PROGRAMME REF: |  | PROGRAMME REF: |  | Project lead
DELIVERABLE (TITLE) | DESCRIPTION | EXCHANGE FORMATS | PROJECT CODE | ORIGINATOR CODE | VOLUME / SYSTEM* | LEVEL/ LOCATION | TYPE | ROLE | NUMBER | CLASSIFICATION (UNICLASS 2015) | NRM1 CODE | OWNER | DATE REQUIRED TO ISSUE | OWNER | DATE REQUIRED TO ISSUE | OWNER | DATE REQUIRED TO ISSUE | OWNER | DATE REQUIRED TO ISSUE | OWNER | DATE REQUIRED TO ISSUE | OWNER | DATE REQUIRED TO ISSUE | OWNER | DATE REQUIRED TO ISSUE | Lead designer
Construction lead
MODELS | [25 empty] | Architect
Civil and structural engineer
Building services engineer
Cost consultant
Contract administrator
Health and safety advisor
Access consultant
Acoustic consultant
Archaeologist
BREEAM assessor
Cladding specialist
Catering consultant
Facilities management (FM) advisor
Fire engineer
Highways consultant
DRAWINGS (CUT FROM MODEL) | [25 empty] | Information manager
Interior designer
Landscape architect
Lighting designer
Masterplanner
Operational lead
Party wall surveyor
Planning consultants
Security advisor
Signage designer
Sustainability advisor
Technical advisor
Other additional project role 1
Other additional project role 2
REPORTS
SPECIFICATIONS
OTHER
* When planning complex projects and determining the number of model files required, it is commonplace and good practice for the project to be divided into volumes defined by coordinates within an overall project model that will be held as separate model files. This enables multiple users to work on the project efficiently. Volumes should be allocated using cut lines to indicate their limits. Volume boundaries could be structural joints or grid lines; for road projects they could be chainage distances; or they could be defined by use e.g. a vertical distribution shaft.